## Project Planner
Optimal Price Prediction for Online Retailers
Start Date: 02 Nov (Literature Search and Review) |  |  |  |  | Period Highlight: | 27 |  |  | Plan Duration | [5 empty] | Actual Start |  |  |  |  | % Complete |  |  |  |  | Actual (beyond plan) | [7 empty] | % Complete (beyond plan)
ACTIVITY | PLAN START | PLAN DURATION | ACTUAL START | ACTUAL DURATION | PERCENT COMPLETE | PERIODS
[6 empty] | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 32 | 33 | 34 | 35 | 36 | 37 | 38 | 39 | 40 | 41 | 42 | 43 | 44 | 45 | 46 | 47 | 48 | 49 | 50 | 51 | 52 | 53 | 54 | 55 | 56 | 57 | 58 | 59 | 60
Literature Search | 1 | 2 | 1 | 6 | 100%
Literature Review | 2 | 6 | 2 | 6 | 100%
Topic Submission Milestone | 5 | 2 | 5 | 2 | 100%
Research Proposal Draft Preparation | 6 | 4 | 6 | 3 | 100%
Research Proposal Overview | 6 | 1 | 7 | 1 | 100%
Research Proposal Submission Milestone | 6 | 4 | 6 | 4 | 100%
Data Pre-Processing | 10 | 2 | 10 | 2 | 100%
Data Cleaning and EDA | 11 | 2 | 10 | 3 | 100%
Manual Feature Extraction | 11 | 3 | 11 | 3 | 100%
Automated Feature Extraction | 12 | 3 | 12 | 3 | 100%
Application of Natural Language Processing Techniques | 13 | 4 | 13 | 4 | 100%
Interim Report Preparation | 14 | 3 | 14 | 3 | 100%
Interim Report Submission | 15 | 1 | 14 | 3 | 100%
Model Building | 19 | 4 | 15 | 9 | 100%
Model Evaluation | 20 | 2 | 16 | 6 | 100%
Parameter Tuning And Re-evaluation | 22 | 2 | 21 | 3 | 100%
Comparative Analysis on Different Machine Learning Models | 23 | 2 | 23 | 2 | 100%
Second Stage Model Building for Dynamic Pricing | 24 | 2 | 24 | 2 | 100%
Re-iterating Parameter Tuning | 25 | 2 | 25 | 2 | 100%
Generating Visual Comaprative Analysis | 25 | 2 | 25 | 2 | 100%
Final Thesis Preparation | 20 | 6 | 20 | 9 | 100%
Results and Conclusion | 26 | 2 | 26 | 2 | 100%
Final Thesis Submission | 27 | 1 | 27 | 1 | 100%
Video Presentation Milestone | 27 | 1 | 27 | 1 | 100%